## Sheet1
Green => Completed, Orange => Need Clarification/to be discussed, Red => Not Yet Started, Yellow => In Process
ACS Consultancy Software
Activities | Modules | Developer Assigned | Roles | Expected Deadline | Remarks on 28th july
MAIN PAGE - Front End | Main Page Front End | New Person ( Ravi) | Super Super Admin |  | Need clarification (new person yet to join)
Landing Page - Advertisement | HR + PMS | Ramesh, Bhavani (Ravi) | Super Admin |  | Need to have a application details
Exams/Questions | OPT Recruiter | Ashwin | Admin
Calender - Schedule | Bench Sales Recruiter | Ashwin | Sub Admin/Sr Manager
Team Calender | Trainer - Schedule/Calendar | Ashwin | Manager |  | Need clarification on module
Cloud Based | Student/Consultant/Employee | Satish | Team Leader
3rd Party Consultant | Student Recruiter | Ashwin | Opt Recruiter |  | Need clarification on module
| Reports |  | Bench Sales
| Accounts India/Accounts USA | Ravi/Ashwin | Trainer |  | Not been discussed
| College | Ramesh | Student/Emp/Consultant
| Consultancy - Multiple | Ramesh | Student Recruiter
| Vendor | Vamshi | Account Head
| Client | Vamshi | Account AR
| Guest House | Ramesh | Account AP
| Statistical Analytics |  | Accountant
| News Feed |  | Vendor
| Attorney | Shiva | Client |  | Not yet started
| Immigration | Shiva | Immigration |  | Not yet started
| Chat | Vamshi | HR
| Development Support |  | Third Party Login
| Hierarchy | Subrat | sr executive |  | Need clarification
| BDM | Subrat
| Third Party Consultancy | Athar |  |  | Not yet started (from Tuesday 1st)
| Login Front End | New Person ( Ravi) |  |  | Need clarification (new person yet to join)
| Calendar | Ashwin
| Admin | Ashwin
| Sub Admin | Ashwin
| Super Admin | Ashwin
| ACS Admin - Super Super Admin | Ashwin
| Forum | Ravi |  |  | Need clarification
| ACS JOBS | Subrat |  | 2017-07-31
| SMS | Satish
| E-Mail | Satish
MIS
Company Finance
Asset Management System
Student Database
New Modules Added on 12-July-2017
| Bench Sales + Bench Sales Out Source | Athar
| Bench Sales Out Source | Athar
| Implementation | Vamshi